## Assumptions
Costing Assumptions & Actuals
Cost of Capital | 8%
Pre- Mobilization | Value
Estimated Cost (Initial) | 214100000
Cost of Bid Document | 5000
EMD (BG) | 4282000
EMD Making Charges (0.80%) | 34256
PBG (BG) | 12800000
PBG Making Charges (0.80%) | 102400
Inflow (As per agreement) | Contract Value | Per Junction Payment (Contract Value/No. of Junctions) | Remarks
Part A - 34 New Junctions | 75518615 | 2221135.7353
Part B - 30 Upgradation | 38471748 | 1282391.6
Part C - 30 PED | 14248796 | 474959.8667
Sum without AMC | 128239159
Part D - AMC | 14248796 |  | For 36 Months starting 03rd Year
Sum with AMC | 142487955
Mobilization Advance | 10% |  | (10% of Contract Value Excluding AMC Value)
Outflow | Cost | Per Junction Cost (Cost/No. of Junctions) | Remarks
Office and Project Engineer per month cost for 6 Month Implementation | 50000 |  | Per month
Penalty during DLP & AMC per month | 12000 |  | As per agreement Rs.2000 Penalty per day for Delay, No. of Days Delay Taken is 6
Cost to Envoys | 94444435 |  | AS per MOU Agreement
Survey Cost | 13072448 |  | Done in Mobilization Period
6 Months Implementation Cost | 81371987 |  | Cost to Envoys - Survey Cost
Part A - 34 New Junctions | 48823192.2 | 1435976.2412
Part B - 30 Upgradation | 24411596.1 | 813719.87
Part C - 30 PED | 8137198.7 | 271239.9567
Control Room Cost | 14000000
CASH FLOW ASSUMPTIONS
Cash Flow is divided into the following periods: Pre-Mobilization Period, Mobilization Period, 6 Months Implementation, Defect Liability Period and AMC
Outflow
a. Pre - Moblization Period: Cost of Bid Document, EMD & PBG Processing Fee
b. Mobilization Period: Survey Cost; Office & Project Engineer per month cost
c. 6 Months Implementation Period:
Month 1: 90% Payment to Envoys for Part A 10 New Junctions; Office & Project Engineer per month cost
Month 2: 90% Payment to Envoys for Part A 10 New Junctions; Office & Project Engineer per month cost
Month 3: 90% Payment to Envoys for Part A 10 New Junctions; Office & Project Engineer per month cost
Month 4: 90% Payment to Envoys for Part A 4 New Junctions, Part B 10 Upgradations & Part C 10 PED; 90% Payment to Vendor for Control Room; Office & Project Engineer per month cost
Month 5: 90% Payment to Envoys for Part B 10 Upgradations & Part C 10 PED; Office & Project Engineer per month cost
Month 6: 90% Payment to Envoys for Part B 10 Upgradations & Part C 10 PED; Office & Project Engineer per month cost
d. DLP
1st Year Q1 to 2nd Year Q3: 6,00,000 Manpower Cost & Quarter Penalty Cost per Quarter
2nd Year Q4 - 6,00,000 Manpower Cost & Quarter Penalty Cost per Quarter; 10% Payment to Envoys for All Junctions; 10% Payment to Vendor for Control Room
e. AMC
1st Year Q1 to 3rd Year Q4: 7,50,000 Manpower Cost & Quarter Penalty Cost Per Quarter
Inflow (As per Agreement)
a. Pre- Mobilization Period: No Payment from Client
b. Mobilization Period: 10% Mobilization Advance of Contract Value excluding AMC Value
c. 6 Months Implementation Period:
Month 1: 80% Payment by client for Part A 10 New Junctions
Month 2: 80% Payment by client for Part A 10 New Junctions
Month 3: 80% Payment by client for Part A 10 New Junctions
Month 4: 80% Payment by client for Part A 4 New Junctions, Part B 10 Upgradations & Part C 10 PED
Month 5: 80% Payment by client for Part B 10 Upgradations & Part C 10 PED
Month 6: 80% Payment by client for Part B 10 Upgradations & Part C 10 PED
d. DLP
1st Year Q1 to 2nd Year Q3: No Payment from Client
2nd Year Q4: 10% Payment by Client of Contract Value excluding AMC Cost
e. AMC
1st Year Q1 - Q4: 27% of AMC Cost; Payment divided per quarter
2nd Year Q1 - Q4: 33% of AMC Cost; Payment divided per quarter
3rd Year Q1 - Q4: 40% of AMC Cost; Payment divided per quarter
Cost of Capital (COC)
a. Pre- Mobilization Period: COC 8% on Running Net
b. Mobilization Period: COC 8% on Running Net
c. 6 Months Implementation Period:
Month 1: COC for 1 Month for initial 70% Payment to Envoys for Supply of Part A 10 New Junctions
Month 2: COC for 1 Month for initial 70% Payment to Envoys for Supply of Part A 10 New Junctions
Month 3: COC for 1 Month for initial 70% Payment to Envoys for Supply of Part A 10 New Junctions
Month 4: COC for 1 Month for initial 70% Payment to Envoys for Supply of Part A 4 New Junctions, Part B 10 Upgradations & Part C 10 PED; COC 8% on Running Net
Month 5: COC for 1 Month for initial 70% Payment to Envoys for Supply of Part B 10 Upgradations & Part C 10 PED
Month 6: COC for 1 Month for initial 70% Payment to Envoys for Supply of Part B 10 Upgradations & Part C 10 PED
d. DLP
1st Year Q1 to 2nd Year Q3: COC 8% on Running Net

## Cash Flow
| Pre - Mobilization Cost | Mobilization | 6 Months Implementation | [5 empty] | DLP1 |  |  |  | DLP2 |  |  |  | AMC 1 |  |  |  | AMC 2 |  |  |  | AMC 3 |  |  |  | Total
Cash Flow |  |  | 1 | 2 | 3 | 4 | 5 | 6 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Inflow (based on Contract Terms) | 0 | 12823915.9 | 17769085.8824 | 17769085.8824 | 17769085.8824 | 21166446.0863 | 14058811.7333 | 14058811.7333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12823915.9 | 961793.75 | 961793.75 | 961793.75 | 961793.75 | 1175525.75 | 1175525.75 | 1175525.75 | 1175525.75 | 1424879.5 | 1424879.5 | 1424879.5 | 1424879.5 | 142487955
Outflow | 141656 | 13122448 | 12973786.1706 | 12973786.1706 | 12973786.1706 | 27584152.9082 | 9814638.44 | 9814638.44 | 636000 | 636000 | 636000 | 636000 | 636000 | 636000 | 636000 | 10173198.7 | 786000 | 786000 | 786000 | 786000 | 786000 | 786000 | 786000 | 786000 | 786000 | 786000 | 786000 | 786000 | 123456091
Running Net | -141656 | -298532.1 | 4795299.7118 | 4795299.7118 | 4795299.7118 | -6417706.822 | 4244173.2933 | 4244173.2933 | -636000 | -636000 | -636000 | -636000 | -636000 | -636000 | -636000 | 2650717.2 | 175793.75 | 175793.75 | 175793.75 | 175793.75 | 389525.75 | 389525.75 | 389525.75 | 389525.75 | 638879.5 | 638879.5 | 638879.5 | 638879.5 | 19031864
COC (8% yearly) on negative | -11332.48 | -23882.568 | -67045.7307 | -67045.7307 | -67045.7307 | -590891.6123 | -50656.7743 | -50656.7743 | -50880 | -50880 | -50880 | -50880 | -50880 | -50880 | -50880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Final Net | -152988.48 | -322414.668 | 4728253.9811 | 4728253.9811 | 4728253.9811 | -7008598.4343 | 4193516.519 | 4193516.519 | -686880 | -686880 | -686880 | -686880 | -686880 | -686880 | -686880 | 2650717.2 | 175793.75 | 175793.75 | 175793.75 | 175793.75 | 389525.75 | 389525.75 | 389525.75 | 389525.75 | 638879.5 | 638879.5 | 638879.5 | 638879.5 | 17747146.5989
Cumulative Final Net | -152988.48 | -475403.148 | 4252850.8331 | 8981104.8141 | 13709358.7952 | 6700760.3609 | 10894276.8799 | 15087793.3989 | 14400913.3989 | 13714033.3989 | 13027153.3989 | 12340273.3989 | 11653393.3989 | 10966513.3989 | 10279633.3989 | 12930350.5989 | 13106144.3489 | 13281938.0989 | 13457731.8489 | 13633525.5989 | 14023051.3489 | 14412577.0989 | 14802102.8489 | 15191628.5989 | 15830508.0989 | 16469387.5989 | 17108267.0989 | 17747146.5989 | 17747146.5989
|  |  | Peak Negative | -7008598.4343
|  |  | Peak Positive | 4728253.9811

## BOQ
JAMMU ATCS PROJECT: COST ESTIMATES & PROFITABILITY
Sr No | ITEM DESCRIPTION | INPUT COST (EXL TAX) | SALE AMNT (EXL TAX) | % MARGIN
1 | Supply, Installation, Testing & Commissioning of field equipments along with 2 years Spare Support & Client Management | 94444435 | 107843386 | 14.19%
2 | Supply, Installation, Testing, Commissioning & setting up of ATCS Control Room with 2 years warranty support(will be done through close-bidding,as done in case of Surat) | 14000000 | 16343808 | 16.74%
3 | 3 Years Annual Maintenance(AMC) Charges | 10575000 | 12601243 | 19.16%
CONTRACT PRICE(EXCL. TAXES) |  | 119019435 | 136788437 | 16.7%
CONTRACT PRICE(INCL. TAXES) |  |  | 142487955
JAMMU ATCS PROJECT: PO TO ENVOYS SUMMARY
Sr No | ITEM DESCRIPTION | REQD QTY | PO RATE(Rs) | TOTAL AMOUNT(Rs)
A) SUPPLY ITEMS
1 | UTCS GEN-II CONTROLLER | 64 | 80250 | 5136000
2 | CDAC ROYALTY | 64 | 15000 | 960000
3 | FLIR VEHICLE DETECTION CAMERA WITH 4TI CARD | 223 | 160165 | 35716795
4 | VEH RED LAMPHEAD | 2837 | 3317 | 9410329
VEH AMBER LAMPHEAD
VEH GREEN LAMPHEAD
PED RED LAMPHEAD
PED GREEN LAMPHEAD
5 | 3 DIGIT CDT | 117 | 8964 | 1048788
6 | 2SQMM/3CORE ARMRD POWER CABLE | 2380 | 81 | 192780
7 | 1.5SQMM/7CORE ARMRD CONTROL CABLE | 23050 | 98 | 2258900
8 | 0.75SQMM/7C UNARMRD FLEXIBLE CABLE | 8440 | 49 | 413560
9 | 1.5SQMM/14CORE ARMRD CONTROL CABLE | 9840 | 166 | 1633440
10 | 3G ROUTER WITH ANTENNA, ADAPTOR & SIM | 64 | 16050 | 1027200
11 | JUNCTION BOX | 617 | 535 | 330095
12 | CANTILEVER POLE 6MTR/3-6-9MTR ARM | 223 | 16050 | 3579150
13 | STANDARD POLE/4MTR WITH BASE PLATE | 373 | 4280 | 1596440
14 | STANDARD POLE/6MTR WITH BASE PLATE | 21 | 6420 | 134820
15 | MOUNTING STRUCTURE | 128 | 2140 | 273920
16 | POWER SUPPLY BOX | 64 | 1605 | 102720
17 | ELCB WITH JUNCTION BOX WITH POLE | 64 | 5350 | 342400
18 | UPS WITH CABINET | 34 | 78110 | 2655740 | TOTAL SUPPLY
19 | 12V/100AH BATTERIES(SET) | 34 | 78993 | 2685762 | 69498839
B) CIVIL ITEMS
20 | TRENCHLESS DUCTING | 9090 | 428 | 3890520
21 | FOUNDATION WORK-CONTROLLER | 64 | 4280 | 273920
22 | FOUNDATION WORK-CANTILEVER POLE | 223 | 12840 | 2863320
23 | FOUNDATION WORK-STANDARD POLE | 394 | 4280 | 1686320 | TOTAL CIVIL
24 | CIVIL WORK(SET) | 94 | 16050 | 1508700 | 10222780
C) SURVEY & SUPPORT
25 | IMPLEMENTATION & SPARE SUPPORT | 64 | 25787 | 1650368 | TOTAL SURVEY
26 | JUNCTION SURVEY & DESIGN | 64 | 204257 | 13072448 | 14722816
|  |  |  | GRAND AMOUNT - FIELD ITEMS | 94444435